## Start Here
GSA Project Plan
Applicant ID:
Phase | Due Date | Status
I. Pre-Independent Evaluation |  | Not Started
II. Independent Evaluation |  | Not Started
III. Pre-Consensus
IV. Consensus
V. Pre-Site Visit
VI. Site Visit
VII. Post Site Visit
Other Key Dates
Business Overview Call
Results Call
Results Call
Results Call
Process Clarification Call

## Template v1 (hidden)
Application #
Site Visit Date:
IE Due Date:
Independent Evaluation
% done | Milestones / Tasks | Who | Est. Duration | Plan Timeframe | Schedule Due Date | Date Completed | Handbook Reference | Stratek Reference | Tools1 | Tools2 | Tools3 | Notes/Comments
I. Preparation
0% | Clarify roles and responsibilities with Backup Team Leader and Category 7 Lead
0% | Send completed Roles & Responsibilities form to Sterling Office and copy team
0% | Complete project plan and send to the Sterling Office
0% | Establish contact with organization
0% | Set up conference call schedule with organization
II. Welcome Each Examiner to the Team
0% | Call each Examiner
0% | Set up team conference calls and prepare for first meeting - set phone number, prepare agenda, calendar, team list and expectations
0% | Send email introducing team and first meeting agenda items (set up email distribution list for the team)
0% | Hold First Team Meeting - encourage introductions, review team list, calendar, expectations, on-going meeting schedule (Be sure to get agreement on dates of consensus meetings, site visit and team conference calls)
III. Expectations and Key Factors Consensus
0% | Communicate Independent Evaluation expectations - assignments, due dates, and deliverables
0% | Complete key factors consensus
0% | Test email communication
IV. Review Independent Evaluation Assignments
0% | Mentor examiners
0% | Receive and Review first items of Independent Scorebook
0% | Receive and review complete independent scorebooks
0% | Provide feedback to each examiner as near to immediate as possible
0% | Set Consensus Meeting Dates
0% | Determine Consensus Assignments
0% | Prepare Scoring Template by updating with each team members scores
0% | Send updated Scoring Template to Sterling Office
0% | Provide Examiner Feedback

## Pre-IE
I. Pre-Independent Evaluation
| IE Due Date: |  |  |  | Site Visit Date: | Applicant ID: | 0
| Task | Status | Schedule Due Date | Date Completed | TL Handbook Reference | Tool 1 | Notes/Comments
I. Preparation
0 | Clarify roles and responsibilities with Backup Team Leader and Category 7 Lead | Not Started |  |  | Leader Roles & Responsibilities
0 | Send completed Roles & Responsibilities form to Sterling Office and copy team | Not Started |  |  | Leader Roles & Responsibilities | Need Leaders Roles and Responsibilities Form | Is there a file that has a list of all of the roles and responsibilities that would be split between the TL and TL backup?
0 | Complete project plan and send to the Sterling Office | Not Started |  |  | Project Plan - page 39 | Project Plan file - this file | Should this be uploaded into Apex versus emailing to Sterling?
0 | Establish contact with organization | Not Started |  |  | Schedule Applicant Conference Calls/Initial Call with the POC
| Assign a mentor to each first year examiner |  |  |  | Leader Roles & Responsibilities
0 | Set up master schedule calendar of calls with team and applicant; including process, results, business overview, leadership roundtable calls) | Not Started |  |  | First Steps | Sample Team Key Dates
II. Welcome Each Examiner to the Team
0 | Call each Examiner individually | Not Started |  |  | Examiner Welcome
0 | Set up team conference calls and prepare for first meeting - set phone number, prepare agenda, calendar, team list and expectations | Not Started |  |  | Team Introductory Call
0 | Send email introducing team and first meeting agenda items (set up email distribution list for the team) | Not Started |  |  | Team Introductory Call | Sample Team Correspondence
0 | Hold First Team Meeting - encourage introductions, review team list, calendar, expectations, on-going meeting schedule | Not Started |  |  | Introduction Team Call | Sample Call Agenda
0 | III. Expectations and Key Factors Consensus
#REF! | Team Leader conducts JITT on inputs, process and outputs of Pre-IE | Not Started
| Conduct business overview call with the organization |  |  |  | Business Overview Call
0 | Complete Key Factors consensus | Not Started |  |  | Key Factors Worksheet
0 | Email, Computer and Apex Testing | Not Started |  |  | Computer Requirements
#VALUE! | Review Apex-Stratex system with team for IE prep | Not Started |  |  | This can be done through JITT by TL and/or Team Apex Champion
#VALUE! | Initiate the IE stage in Apex | Not Started
Note on C3: Amielee Farrell: When Completed is selected a checkmark will appear in Column A

## IE
II. Independent Evaluation
| IE Due Date: |  |  |  | Site Visit Date: | Applicant ID: | 0
| Task | Status | Schedule Due Date | Date Completed | TL Handbook Reference | Tool 1 | Notes/Comments
0 | I. Review Independent Evaluation Assignments
0 | Team Lead conducts a JITT on inputs, process and outputs of IE for the team | Not Started |  |  | Examiner Mentoring
| TL and/or Back up TL review at least 1 strength and 1 OFI for all new examiners early on in IE process | Not Started |  |  | Examiner Mentoring | Sample Examiner Feedback
0 | TL and/or Back up TL provide feedback to each examiner throughout IE process by checking IE comments in Apex | Not Started |  |  | Review Process Items and Provide Feedback | Sample Examiner Feedback
0 | Prepare Scoring Template by updating with each team members scores | Not Started |  |  |  |  | Is this now done is Apex?
0 | Send updated Scoring Template to Sterling Office | Not Started |  |  |  |  | Is this now done is Apex?
0 | Provide Examiner Feedback | Not Started |  |  | Review Final IE scorebooks
0 | Determine and Communicate Category/Item Lead & Backup Assignments | Not Started |  |  | Consesnus Considerations
0 | Review Apex-Stratex system with team for Consensus Prep | Not Started |  |  | This can be done through JITT by TL and/or Team Apex Champion
0 | Initiate the Consensus stage in Apex | Not Started
Note on C3: Amielee Farrell: When Completed is selected a checkmark will appear in Column A

## Pre-Consensus
III. Consensus Preparation
| Due Date: | 2019-02-15 |  |  | Site Visit Date: | Applicant ID: | 0
| Task | Status | Schedule Due Date | Date Completed | TL Handbook Reference | Tool 1 | Notes/Comments
I.Consensus Preparation
0 | Team Lead conducts a JITT on inputs, process and outputs of Pre-Consensus | Not Started |  |  | Conduct Consensus Preparation Team Call
| Review Team Virtual Protocols | Not Started |  |  | Conference Call/Video Protocols
0 | Review Examiner Consensus Comments | Not Started |  |  | Review Prelimiary Synthiesis and Provide Feedback
0 | Review and Update Consensus Key Factors Worksheet | Not Started |  |  | Refine Key Factors
| Review Organization Documents | Not Started |  |  | Review Applicant Documents
0 | Prepare for Process Calls | Not Started |  |  | Prepare Interview Questions
| Conduct the Process Calls | Not Started
0 | Prepare Draft Executive Summary Worksheet | Not Started |  |  | Draft Executive Summary
Note on B12: %username%: What is this? Not sure we still do this

## Consensus
IV. Consensus
| Due Date: | #REF! |  |  | Site Visit Date: | Applicant ID: | 0
| Task | Status | Schedule Due Date | Date Completed | TL Handbook Reference | Tool 1 | Notes/Comments
Consensus Meeting
0 | Prepare consensus agenda | Not Started |  |  | Prepare Consensus Agenda | Sample Team Consensus Agenda
| Assign Team Roles |  |  |  | Assign Roles
0 | Set Deadlines for Scorebook Revisions | Not Started |  |  | Set Date for Revised Worksheets
0 | Provide Feedback to Team | Not Started |  |  | Provide Examiner Feedback | Sample Examiner Feedback
| Project Plan |  |  |  | Update the Project Plan
0 | Prepare Draft Executive Summary Worksheet | Not Started |  |  | Draft Executive Summary | Sample Executive Summary Worksheet
0 | Site Visit Preparation | Not Started
0 | Review Apex-Stratex system with team for Site Visit Prep | Not Started |  |  | This can be done through JITT by TL and/or Team Apex Champion
0 | Initiate the Site Visit stage in Apex | Not Started
Note on B10: %username%: What is this? Not sure we still do this

## Pre-Site Visit
V. Site Visit Preparation
| Due Date: | #REF! |  |  | Site Visit Date: | Applicant ID: | 0
| Task | Status | Schedule Due Date | Date Completed | TL Handbook Reference | Tool 1 | Notes/Comments
I. Preparation
0 | Communicate with the Organization Point of Contact | Not Started |  |  | Continue Frequent Contact/Facillities Location/Site Visit Schedules
0 | Interview Request List | Not Started |  |  | Interview Request List
0 | Begin Site Visit Strategy | Not Started |  |  | Site Visit Overview/Conduct Site Visit Preparation
0 | TL conducts Conduct JITT on Site Visit comments | Not Started |  |  | Training
0 | Ensure appropriate people are going to be interviewed | Not Started |  |  | People to Interview
0 | Prepare Interview Schedules and Evening Meetings | Not Started |  |  | Interview Schedules/Evening Team Status Meetings | Sample Interview Plan/Sample Team Schedules and Agendas/Same Evening Team Meetings
0 | Review Examiner Strategy | Not Started |  |  | Examiner Preparation/Strategy Review

## SV
VI. Site Visit
| Site Visit Date: |  | #REF! |  |  | Applicant ID: | 0
| Task | Status | Schedule Due Date | Date Completed | TL Handbook Reference | Tool 1 | Notes/Comments
Conduct Site Visit
0 | Conduct Pre-Site Planning Meeting and training using PowerPoint | Not Started |  |  | Pre-Site Plannig Meeting
0 | Introduction to Applicant Point of Contact | Not Started |  |  | Point of Contact
0 | Ensure Examiner Preparation | Not Started |  |  | Examiner Preparation
| JITT for Site Visit | Not Started |  |  | Training
0 | Conduct Opening Meeting / Executive In-Brief (Includes applicant presentation) | Not Started |  |  | Opening Meeting
0 | Conduct Daily Debriefs | Not Started |  |  | Daily Debriefs/Day 1, Day 2, Day 3 Status briefs
0 | Lead Evening Status Meetings | Not Started |  |  | Evenign Status meetings
0 | Review Scoring | Not Started |  |  | Revisit Site Visit Scoring
0 | Review Interview Scripts and Schedules | Not Started |  |  | Udpate Interview Scripts and Schedules
0 | Reach Consensus | Not Started |  |  | Site Visit Consensus
| Write Final Feedback | Not Started |  |  | Final Feedback Comments
| Determine Final Scores | Not Started |  |  | Final Scoring
0 | Finalize Executive summary | Not Started |  |  | Update Executive Summary
0 | Prepare Executive Out-Brief | Not Started |  |  | Prepare Executive Out-Brief
0 | Deliver Executive Out-Brief | Not Started |  |  | Deliver Executive Out-Brief
| Complete Sterling Best Practice | Not Started |  |  | Complete Sterling Best Practice
0 |  | Not Started

## Post SV
VII. Post Site Visit
| Site Visit Date: |  | #REF! |  |  | Applicant ID: | 0
| Task | Status | Schedule Due Date | Date Completed | TL Handbook Reference | Tool 1 | Notes/Comments
Post Site Visit
0 | Complete Examiner Evaluations | Not Started |  |  | Complete Examiner Evaluations
0 | Send Evaluations to Sterling | Not Started |  |  | Site Visit Checklist
0 | Team Farewell | Not Started |  |  | Say Goodbye
0 | Thank You Notes | Not Started |  |  | Send Thank you Notes
0 | Submit Deliverables to Sterling - Final | Not Started |  |  | Site Visit Checklist
0 | Be Available to Answer Questions | Not Started |  |  | Be Available to Answer Questions
0 | Shred/Delete Organization-Related Files | Not Started |  |  | Shred/Delete Organization-Related Files
0 | Receive notification of judge review completion | Not Started
0 | Notify every team member to delete/destroy and notify you when complete | Not Started |  |  | Examiner Notes Materials
0 | Destroy documents once notified by Sterling Office or Team Leader | Not Started
0 | Confirm response from all team members | Not Started
0 | Send completed Project Plan to Sterling office. Congratulations! | Not Started

## Results
Results Phase | Process Phase
Application Review
Synthesize Key factors | IE
Read the Application | IE
Clarify/Verify Existing Results | IE
Compile Expected Results | IE/Consensus Prep
Results Analysis
7.1
Preliminary Analysis | Consensus Prep- SV Prep
Formulate Questions | Consensus Prep- SV Prep
Results Calls | Consensus Prep- SV Prep
Review Responses | Consensus Prep- SV Prep
Write Example | Consensus Prep- SV Prep
Group Examples | SV Prep
Write Final Comment | SV Prep
7.2
Preliminary Analysis | Consensus Prep- SV Prep
Formulate Questions | Consensus Prep- SV Prep
Results Calls | Consensus Prep- SV Prep
Review Responses | Consensus Prep- SV Prep
Write Example | Consensus Prep- SV Prep
Group Examples | SV Prep
Write Final Comment | SV Prep
7.3
Preliminary Analysis | Consensus Prep- SV Prep
Formulate Questions | Consensus Prep- SV Prep
Results Calls | Consensus Prep- SV Prep
Review Responses | Consensus Prep- SV Prep
Write Example | Consensus Prep- SV Prep
Group Examples | SV Prep
Write Final Comment | SV Prep
7.4
Preliminary Analysis | Consensus Prep- SV Prep
Formulate Questions | Consensus Prep- SV Prep
Results Calls | Consensus Prep- SV Prep
Review Responses | Consensus Prep- SV Prep
Write Example | Consensus Prep- SV Prep
Group Examples | SV Prep
Write Final Comment | SV Prep
7.5
Preliminary Analysis | Consensus Prep- SV Prep
Formulate Questions | Consensus Prep- SV Prep
Results Calls | Consensus Prep- SV Prep
Review Responses | Consensus Prep- SV Prep
Write Example | Consensus Prep- SV Prep
Group Examples | SV Prep
Write Final Comment | SV Prep
Finalize Comments
Consensus on Comments | SV
Final Correlation with Process Comments | SV
Final Review | SV-Post SV
Support Process Categories
Support Category 1 with Item 7.4 | Consensus - Post SV
Support Category 2 with Items 7.4&5 | Consensus - Post SV
Support Category 3 with Items 7.2&5 | Consensus - Post SV
Support Category 4 with Comparisons | Consensus - Post SV
Support Category 5 with Item 7.3 | Consensus - Post SV
Support Category 6 with Item 7.1 | Consensus - Post SV