## Plan
Improvement Projects/Action Plans for EMS Objectives &Targets or Strategic Plan goals
Project Title: |  | Employee Mobility Achievement Program (EMAP)
Description: |  | EMAP is the City of Tallahassee’s succession planning program.
Scope: |  | The expected outcome of this program is a pool of qualified candidates for critical positions in: • Professional and Managerial-supervisory (i.e., professionals, managers and middle managers, and first- and second-line supervisors) • Occupational discipline (i.e., administrative and technical)
Objective: |  | COT is firmly committed to helping employees develop their potential so that they are prepared and qualified to assume positions in line with managerial, executive level, technical and organizational needs. Employees identified to participate in the Employee Mobility Achievement Program (EMAP) must be committed to the philosophy of the city's mission, vision, and organizational values.
Related EMS Target or SBP Goal: |  | Develop a structured approach to meet anticipated vacancies in key positions. Provide a process that: a) prepares employees to be ready to fill key positions; b) fosters employee promotability options within the COT; c) preserves institutional knowledge.
Measurement (if defined): (Description of Outcome) |  | At least two or more job-ready candidates to fill key jobs when they become vacant; • Thirty percent (30%) of jobs will be filled by internal candidates; • Reduce the time it takes to fill a job (compared to externally) by 4 weeks by preparing and selecting from internal candidates; • Lower cost by fifty percent (50%) of advertising and recruiting for external hires; •Eighty five percent (85%) completion rate of activities outlined in IDP for each employee. • Establish a minimum of two years retention in critical jobs of identified EMAP successors; • The creation of one hundred percent (100%) quality Individual Development Plans (IDP) with activities for gaining the needed competencies.
Baseline (if available): |  | At the program’s inception, more than fifty percent (50%) of COT employees were 44 years old or older, and fourteen percent (14%) were 55 years or older. More than seven hundred (700) employees were eligible for retirement. The trend of an aging workforce continues with retirement projections for 2013-2020 , there are now 587 (33%) non sworn employees eligible for retirement. Water Utilities has ninety one (91) or twenty eight percent (28%) of the department's employees as potential retirees for this period. Most of these positions are considered key and hard to fill. Among the positions are: Underground Utilities System Operator, Microbiologist, Supervisor for Analytical Chemistry Lab and Wastewater Plant Operator A, to name a few.
Project Initiation Date: |  | 2014-05-01
Completion Dates: |  | Planned: | 2015-09-30 | Revised: |  | Actual:
Timeline Planning Increments (in Days) |  | 30 | (Planning Increments will be reflected on the "Do" tab chart
Project Sponsor\Champion |  | Mike Tadros
Implementation Team / Division Lead: |  | Underground Utilities
Project Manager/ Team Lead: |  | Gordon Klein
Steering Team Members: |  | Jim Oskowis |  | John Buss |  | Jodie Cahoon
|  | Stephen Mayfield |  | Jon Kilpatrick
Anthony Moore
Working Team Members: |  | Gordon Klein |  | Diedra Lane |  | Blas Gomez
|  | Charles Ziegmont |  | Jamie Shakar
Project Dates
Task No. | Task Description | Lead Staff | Start | Expected Completion | Actual Completion | Barriers | Deliverable / Outcome
1 | Team Kickoff | Klein | 2014-06-04 | 2014-06-04 | 2014-06-04 | Availability
2 | Identify critical jobs | Managers | 2014-06-04 | 2014-06-13 |  | Dependent on mangers completing their employee surveys. | List of critical positions in a priority order.
3 | Garnish critical competencies | Lead 3
4 | Create "Assessment" survey | Lead 4
5 | Identify potential employees for the program | Lead 5
6 | Assess employees for critical competencies | Lead 6
7 | Create employee Individual Development Plan | Lead 7
8 | Enroll employee in the developmental activities | Lead 8
9 | Monitor employee progress (60 day debriefing) | Lead 9
10 | Advance employee to EMAP "ready pool" | Lead 10
Formulas:
Revised: = [Start]

## Do
| Project Title: | Employee Mobility Achievement Program (EMAP)
| Objective: | COT is firmly committed to helping employees develop their potential so that they are prepared and qualified to assume positions in line with managerial, executive level, technical and organizational needs. Employees identified to participate in the Employee Mobility Achievement Program (EMAP) must be committed to the philosophy of the city's mission, vision, and organizational values.
| SBP goal or EMS target | Develop a structured approach to meet anticipated vacancies in key positions. Provide a process that: a) prepares employees to be ready to fill key positions; b) fosters employee promotability options within the COT; c) preserves institutional knowledge.
ID | Project Name | Owner | Recources | Start | End | 2014-05-01 | 2014-05-31 | 2014-06-30 | 2014-07-30 | 2014-08-29 | 2014-09-28 | 2014-10-28 | 2014-11-27 | 2014-12-27 | 2015-01-26 | 2015-02-25 | 2015-03-27 | 2015-04-26 | 2015-05-26 | 2015-06-25 | 2015-07-25 | 2015-08-24 | 2015-09-23 | 2015-10-23
| Employee Mobility Achievement Program (EMAP) | Gordon Klein |  | 2014-05-01 | 2015-09-30
1 | Team Kickoff | Klein |  | 2014-06-04 | 2014-06-04
1.1.1
1.1.2
1.1.3
2 | Identify critical jobs | Managers |  | 2014-06-04 | 2014-06-13
2.1 | WRE surveys incomplete | Buss / Gomez |  | 2014-06-13 | 2014-09-18
2.2 | Review listing and prioritize | Team | completed surveys | 2014-09-18 | 2014-10-15
2.3
3 | Garnish critical competencies | Lead 3 |  | 0 | 0
3.1
3.2
3.3
4 | Create "Assessment" survey | Lead 4 |  | 0 | 0
4.1
4.2
4.3
5 | Identify potential employees for the program | Lead 5 |  | 0 | 0
5.1
5.2
5.3
6 | Assess employees for critical competencies | Lead 6 |  | 0 | 0
6.1
6.2
6.3
7 | Create employee Individual Development Plan | Lead 7 |  | 0 | 0
7.1
7.2
7.3
8 | Enroll employee in the developmental activities | Lead 8 |  | 0 | 0
8.1
8.2
8.3
9 | Monitor employee progress (60 day debriefing) | Lead 9 |  | 0 | 0
9.1
9.2
9.3
10 | Advance employee to EMAP "ready pool" | Lead 10 |  | 0 | 0
10.1
10.2
10.3

## Check
Project Title: |  | Employee Mobility Achievement Program (EMAP)
Objective: |  | COT is firmly committed to helping employees develop their potential so that they are prepared and qualified to assume positions in line with managerial, executive level, technical and organizational needs. Employees identified to participate in the Employee Mobility Achievement Program (EMAP) must be committed to the philosophy of the city's mission, vision, and organizational values.
SBP goal or EMS target: |  | Develop a structured approach to meet anticipated vacancies in key positions. Provide a process that: a) prepares employees to be ready to fill key positions; b) fosters employee promotability options within the COT; c) preserves institutional knowledge.
Comments regarding the Project or Task Completion/Duration Date Revisions:
Task No. | Task Description | Lead Staff | Comments
1 | Team Kickoff | Klein
2 | Identify critical jobs | Managers
3 | Garnish critical competencies | Lead 3
4 | Create "Assessment" survey | Lead 4
5 | Identify potential employees for the program | Lead 5
6 | Assess employees for critical competencies | Lead 6
7 | Create employee Individual Development Plan | Lead 7
8 | Enroll employee in the developmental activities | Lead 8
9 | Monitor employee progress (60 day debriefing) | Lead 9
10 | Advance employee to EMAP "ready pool" | Lead 10

## Act
Project Title: | Employee Mobility Achievement Program (EMAP)
Objective: | The expected outcome of this program is a pool of qualified candidates for critical positions in: • Professional and Managerial-supervisory (i.e., professionals, managers and middle managers, and first- and second-line supervisors) • Occupational discipline (i.e., administrative and technical)
SBP goal or EMS target: | COT is firmly committed to helping employees develop their potential so that they are prepared and qualified to assume positions in line with managerial, executive level, technical and organizational needs. Employees identified to participate in the Employee Mobility Achievement Program (EMAP) must be committed to the philosophy of the city's mission, vision, and organizational values.
Total Project Time (in days):
What was the Return on Investment?
Lessons Learned:
CLOSE OUT SIGNATURES
Project Sponsor\Champion
Implementation Team (EMR)/ Division Lead:
Project Manager:

## KPIs
Focus | KPI | Indicator Expectation | Notes | Units | Baseline | FY14 Target | FY14 | FY15 Target | FY15 | FY16 Target | FY16
EMPLOYEE
Employee | Pct of Key Jobs with at least 2 established Individual Development Plans (IDPs) | i | Baseline will be zero and will rise as the Succession Planning is implemented. | Pct | 0 | 50% |  | 75% |  | 100%
Employee | Pct of UU staff with a IDP/Succession Plan (including those established for jobs not identified as "key") | i | Baseline will be zero and will rise as the Succession Planning is implemented. | Pct | 0 | 5% |  | 10% |  | 25%
Employee | Individual Development Plan Completion Rate | i | Baseline will be zero and will rise as the Succession Planning is implemented. | Pct | 0 | 25% |  | 50% |  | 85%
Employee | Pct of key jobs filled by internal candidates | i |  | Pct | ? | 20% |  | 25% |  | 30%
Employee | Advancement rate of staff with IDP | i | Baseline will be zero and will rise as the Succession Planning is implemented. | Pct | 0 | 5% |  | 10% |  | 15%
Employee | Number of job ready candidates applying for key jobs | i |  | Number |  | 0.02 |  | 0.1 |  | 0.15
Employee | Job Retention | i | Establish minimum of 2 years for Succession Plan hires | Years |  | 1 |  | 2 |  | 3
COSTS
Employee / Costs | Turnover rate (within and outside of staff with Plan) | k | Expect turnover rates to decrease overtime if compensation is competitive. Costs for recruitment and new hire training avoided. | Pct | 9% | 8% |  | 7% |  | 6%
Costs | Time to fill key jobs | k | Reduction in recruitment time (vacancy time) by 4 weeks. | Weeks |  | 2 |  | 3 |  | 4
Costs | Advertising and recruiting costs | k | Reduction costs to advertise | Pct |  | 25% |  | 35% |  | 50%

## Meeting Notes
Date | Agenda | Notes
2014-06-04 | Tentative Meeting Agenda • Review SBP goal and background of project • Review project scope and objective • Review Project tasks and timeline • Identify project team members • Schedule next meeting | *Each Manager will identify critical positions (titles) -specialized knowledge or skill with limited staff capable of performing - Due to Gordon by Friday 6/13/14 COB *Steering Committee:Jon, Stephen, Jim, John, Jodie, Anthony plus working team *Working Team: Blas, Gordon, Jamie, Emerson, Chuck *Steering committee to meet monthly *Schedule working team meeting for week of 6/9
2014-08-22 | Manager's were sent surveys of all P1 position employees; *review preliminary results (Cody) | *Complete employee surveys by 8/29/14 (Gemini employees needed); * schedule next meeting for 9/18/14 PM (JBR) * Replace Emerson from working team with Diedra Lane; * next step is to identify list of critical positions.
2014-09-18 | Pickup our discussions of the survey assessment tool and identify the critical positions. | Postponed the 9/18 meeting until after Manager's retreat that is scheduled for 9/24-9/25. Surveys for Gemini employees are still incomplete.
2014-10-09 | Attendees: Shakar, Buss, Gomez, Klein, Ziegmont, Walden, and Lane *Discuss survey and re-focus of project | * Complete surveys for Gemini Positions and provide data to Gordon (Blas lead); * Create DRAFT critical position based on surveys and distribute to working team and then provide to Steering committee(Gordon lead); * Schedule meeting with Steering committee (Chuck); * Discuss survey results and criticality list; * Review and discuss scope/objective of Project; * Identify steps (process) for project
2015-04-10 | Attendees: Shakar, Buss, Gomez, Klein, Ziegmont, Pugh, and Lane *Discuss survey and re-focus of project | * Create DRAFT critical position based on surveys and distribute to working team and then provide to Steering committee(Gordon lead); * Schedule meeting with Steering committee (Chuck); * Discuss survey results and criticality list; * Review and discuss scope/objective of Project; * Identify steps (process) for project
2015-05-15 | Attendees: Shakar, Buss, Gomez, Klein, Ziegmont, Pugh, and Lane *Discuss updated critical position list survey and re-focus of project | * Create DRAFT critical position based on surveys and distribute to working team and then provide to Steering committee(Gordon lead); * Schedule meeting with Steering committee (Chuck); * Discuss survey results and criticality list; * Review and discuss scope/objective of Project; * Identify steps (process) for project

## Rothwell Plan
http://ucsfhr.ucsf.edu/files/The_Nuts_Bolts_of_Succession_Planning.pdf